## Intro-Flag
CO3 Model for Control of Traffic During Construction
This model is for modeling traffic delay, user cost, and construction cost for construction and maintenance operations.
CO3 Flag models common flagging operations, in which traffic in two directions shares one lane, with traffic forming a queue in one direction while traffic moves in the other direction in the single lane.
This model parallels the more general CO3, which is in CO.xls (see), which is to be used when traffic in each direction has at least one lane of its own.
CO3 was created by Robert I. Carr under a grant from the Michigan Department of Transportation to provide better service to the traveling public.
Copyright Robert I.Carr, 1997
Department of Civil and Environmental Engineering
University of Michigan
Ann Arbor, MI 48109-2125
Email: RICarr@umich.edu
Phone (313) 764-9420 Fax (313) 764-4292
RICarr on 17 Feb 98: Corrected error for car user cost per hour not equal to truck user cost per hour.
RICarr on 21 May 99: Added calculation of backup delay for vehicles arriving after flagging due to backup at end of flagging.
BFKrom on 24 June 2010: Corrected error where traffic backup data was being carried over between method computations, causing error in the outputs.

## flag
SummaryView - Flagging Operation
|  |  | period length (min) | 60 |  | PROJECT INFORMATION | [5 empty] | REPORT INFORMATION
|  |  | annual traffic growth (%) |  |  | PROJECT | [5 empty] | REPORT | DETAILED USER COST REPORT
|  |  | years of growth |  |  | TITLE | [5 empty] | TITLE | SUMMARY VIEW
VEHICLE INPUT |  |  | cars | trucks |  |  | C.S. | [5 empty] | DIVISION
|  | design demand (%) | 100% |  |  |  | JOB # | [5 empty] | REPORT BY
|  | user cost per hour ($/V hr) | 17.98 | 31.73 |  |  | START DATE | [5 empty] | REPORT DATE
|  | user cost per mile, ($/V mi) | 0.575 | 1.87 |  | NOTES:
user cost per cancellation, ($/V)
METHOD INPUT | [5 empty] | METHOD 1 |  |  | METHOD 2 |  |  | METHOD 3 |  |  | METHOD 4
method title
DISTANCE AND SPEED INPUTS |  |  |  | (mi) (mph) |  | distance | speed |  | distance | speed |  | distance | speed |  | distance | speed
|  | work zone |  | method travel
normal travel
|  | diversion |  | method travel
normal travel
FLAG OPERATION INPUTS
|  |  |  | vehicle headway at gate (sec) |  | 3 |  |  | 3 |  |  | 3 |  |  | 3
|  |  |  | dead time at gate when direction changes (sec) |  | 15 |  |  | 15 |  |  | 15 |  |  | 15
allowable gate closed time (min.)
DECREASE TO DEMAND
canceled cars (with no delay) (%)
canceled trucks (with no delay) (%)
canceled cars (with delay) (%/min)
canceled trucks (with delay) (%/min)
diverted cars (with no delay) (%)
diverted trucks (with no delay) (%)
diverted cars (with delay) (%/min)
diverted trucks (with delay) (%/min)
OTHER USER COST INPUT | [5 empty] | cars | trucks |  | cars | trucks |  | cars | trucks |  | cars | trucks
|  |  |  | other user cost per actual demand ($/V) |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | user cost per diversion ($/V) |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
PERIOD INPUT (V/period) |  |  | (Backup at Start of Flagging) Flag Periods (Capacity at End of Flagging) Demand
direction: |  |  | Both Directions |  |  | (Bsof) Flag | demand |  | (Bsof) Flag | demand |  | (Bsof) Flag | demand |  | (Bsof) Flag | demand
period | historical |  |  | design |  | (Ceof) | actual |  | (Ceof) | actual |  | (Ceof) | actual |  | (Ceof) | actual
0 |  |  | 0 | 0
1 A |  |  | 0 | 0
2 A |  |  | 0 | 0
3 A |  |  | 0 | 0
4 A |  |  | 0 | 0
5 A |  |  | 0 | 0
6 A |  |  | 0 | 0
7 A |  |  | 0 | 0
8 A |  |  | 0 | 0
9 A |  |  | 0 | 0
10 A |  |  | 0 | 0
11 A |  |  | 0 | 0
12 P |  |  | 0 | 0
1 P |  |  | 0 | 0
2 P |  |  | 0 | 0
3 P |  |  | 0 | 0
4 P |  |  | 0 | 0
5 P |  |  | 0 | 0
6 P |  |  | 0 | 0
7 P |  |  | 0 | 0
8 P |  |  | 0 | 0
9 P |  |  | 0 | 0
10 P |  |  | 0 | 0
11 P |  |  | 0 | 0
Total | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
SUMMARY OUTPUT |  |  |  | traffic method
[6 empty] | Flagging |  |  | Flagging |  |  | Flagging |  |  | Flagging
|  |  |  | total user cost |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | user cost of delays |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | user cost of decreases |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum backup (V) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum backup length (lane mi) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum delay (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | average delay, except diversions (min) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total delay, except diversions (V hr) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total vehicles canceled(V) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total vehicles diverted (V) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total decrease in demand (V) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | % decrease in demand |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
|  |  |  | delay per diverted vehicle (min) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total diversion delay (V hr) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | average delay, including diversions (min) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | total delay, including diversions (V hr) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | user cost / design demand |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | delay cost / actual demand |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | work zone method travel time (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | speed delay (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum capacity (V/hr) |  | 2400.04 |  |  | 2400.04 |  |  | 2400.04 |  |  | 2400.04
|  |  |  | gate delay at maximum capacity (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum gate and speed delay (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | maximum backup delay (min.) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
OK |  |  |  | validity of output |  | NOT VALID |  |  | NOT VALID |  |  | NOT VALID |  |  | NOT VALID
Overall View - Flagging Operation
|  |  | period length (min) | 60 |  | PROJECT INFORMATION | [5 empty] | REPORT INFORMATION
|  |  | annual traffic growth (%) |  |  | PROJECT | [5 empty] | REPORT | DETAILED USER COST REPORT
|  |  | years of growth |  |  | TITLE | [5 empty] | TITLE | OVERALL VIEW
VEHICLE INPUT |  |  | cars | trucks |  |  | C.S. | 33081 |  |  |  |  | DIVISION
|  | design demand (%) | 100% |  |  |  | JOB # | [5 empty] | REPORT BY
|  | user cost per hour ($/V hr) | 11.41 | 11.41 |  |  | START DATE | 1997-04-30 |  |  |  |  | REPORT DATE
|  | user cost per mile, ($/V mi) | 0.3 | 1 |  |  |  |  | SUMMARY OUTPUT | [6 empty] | traffic method
|  | user cost per cancellation, ($/V) | [13 empty] | total user cost | 0
METHOD INPUT | [5 empty] | METHOD 4 | [9 empty] | user cost of delays | 0
|  |  |  | method title | [11 empty] | user cost of decreases | 0
DISTANCE AND SPEED |  |  |  | (mi) (mph) |  | distance | speed | [8 empty] | maximum backup (V) | 0
|  | work zone |  | method travel | [11 empty] | maximum backup length (lane mi) | 0
|  |  |  | normal travel | [11 empty] | maximum delay (min.) | 0
|  | diversion |  | method travel | [11 empty] | average delay, except diversions (min) | 0
|  |  |  | normal travel | [11 empty] | total delay, except diversions (V hr) | 0
SPEED DELAY INPUT | [15 empty] | total vehicles canceled(V) | 0
|  |  |  | vehicle headway at gate (sec) |  | 3 | [9 empty] | total vehicles diverted (V) | 0
|  |  |  | dead time at gate when direction changes (sec) |  | 15 | [9 empty] | total decrease in demand (V) | 0
|  |  |  | allowable gate closed time (min.) | [11 empty] | % decrease in demand | 0%
DECREASE TO DEMAND INPUT | [15 empty] | delay per diverted vehicle (min) | 0
|  |  |  | canceled cars (with no delay) (%) | [11 empty] | total diversion delay (V hr) | 0
|  |  |  | canceled trucks (with no delay) (%) | [11 empty] | average delay, including diversions (min) | 0
|  |  |  | canceled cars (with delay) (%/min) | [11 empty] | total delay, including diversions (V hr) | 0
|  |  |  | canceled trucks (with delay) (%/min) | [11 empty] | user cost / design demand | 0
|  |  |  | diverted cars (with no delay) (%) | [11 empty] | delay cost / actual demand | 0
|  |  |  | diverted trucks (with no delay) (%) | 2 | [10 empty] | work zone method travel time (min.) | 0
|  |  |  | diverted cars (with delay) (%/min) | 2 | [10 empty] | speed delay (min.) | 0
|  |  |  | diverted trucks (with delay) (%/min) | [11 empty] | maximum capacity (V/hr) | 2400.04
OTHER USER COST INPUT | [5 empty] | cars | trucks | [8 empty] | gate delay at maximum capacity (min.) | 0
|  |  |  | other user cost per actual demand ($/V) |  | 0 | 0 | [8 empty] | maximum gate and speed delay (min.) | 0
|  |  |  | user cost per diversion ($/V) |  | 0 | 0 | [8 empty] | maximum backup delay (min.) | 0
DEMAND INPUT |  |  |  |  | 60 | backup | backup |  | maximum | total |  | average | average |  | average |  | user cost | delay cost
period | hist. | design | Flag | actual |  |  | length |  | delay | period |  | backup | zone |  | delay |  | / design | / actual
| demand | demand |  | demand |  | eop | eop |  |  | delay |  | delay | delay |  |  |  | demand | demand
(hr) | (V/period) | (V/period) |  | (V/period) |  | (V) | (lane.mile) |  | (min) | (Vhr) |  | (min) | (min) |  | (min) |  | ($/V) | ($/V)
0 | 0 | 0 |  |  | 0.1
1 A | 0 | 0 |  |  | 10.79
2 A | 0 | 0 |  |  | 0.5
3 A | 0 | 0 |  |  | 10
4 A | 0 | 0
5 A | 0 | 0
6 A | 0 | 0
7 A | 0 | 0
8 A | 0 | 0
9 A | 0 | 0
10 A | 0 | 0
11 A | 0 | 0
12 P | 0 | 0
1 P | 0 | 0
2 P | 0 | 0
3 P | 0 | 0
4 P | 0 | 0
5 P | 0 | 0
6 P | 0 | 0
7 P | 0 | 0
8 P | 0 | 0
9 P | 0 | 0
10 P | 0 | 0
11 P | 0 | 0
TOT | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | AVG | 0 | 0
MAX | 0 | 0 | 0 | 0 | 10.79 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | MAX | 0 | 0
MIN | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | MIN | 0 | 0
period | canceled | canceled | diverted | diverted |  | decrease | decrease |  | total | decrease |  | decrease | delay |  | delay | decrease | delay | user
| cars | trucks | cars | trucks |  | to | to |  | period | cost |  | cost | cost |  | cost | cost | cost | cost
[6 empty] | cars | trucks |  | decrease | cars |  | trucks | cars |  | trucks
(hr) | (V) | (V) | (V) | (V) |  | (V/period) | (V/period) |  | (V/period) | ($) |  | ($) | ($) |  | ($) | ($) | ($) | ($)
0
1 A
2 A
3 A
4 A
5 A
6 A
7 A
8 A
9 A
10 A
11 A
12 P
1 P
2 P
3 P
4 P
5 P
6 P
7 P
8 P
9 P
10 P
11 P
TOT | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
MAX | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
MIN | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
Traffic View - Flagging Operation
|  |  | period length (min) | 60 |  | PROJECT INFORMATION | [5 empty] | REPORT INFORMATION
|  |  | annual traffic growth (%) |  |  | PROJECT | [5 empty] | REPORT | DETAILED USER COST REPORT
|  |  | years of growth |  |  | TITLE | [5 empty] | TITLE | TRAFFIC VIEW
VEHICLE INPUT |  |  | cars | trucks |  |  | C.S. | 33081 |  |  |  |  | DIVISION
|  | design demand (%) | 100% |  |  |  | JOB # | [5 empty] | REPORT BY
|  | user cost per hour ($/V hr) | 11.41 | 11.41 |  |  | START DATE | 1997-04-30 |  |  |  |  | REPORT DATE
|  | user cost per mile, ($/V mi) | 0.3 | 1 |  |  |  |  | SUMMARY OUTPUT |  |  |  | traffic method
|  | user cost per cancellation, ($/V) | [10 empty] | total user cost |  | 0
METHOD INPUT | [5 empty] | METHOD 1 | [6 empty] | user cost of delays |  | 0
|  |  |  | method title | [8 empty] | user cost of decreases |  | 0
DISTANCE AND SPEED |  |  |  | (mi) (mph) |  | distance | speed | [5 empty] | maximum backup (V) |  | 0
|  | work zone |  | method travel | [8 empty] | maximum backup length (lane mi) |  | 0
|  |  |  | normal travel | [8 empty] | maximum delay (min.) |  | 0
|  | diversion |  | method travel | [8 empty] | average delay, except diversions (min) |  | 0
|  |  |  | normal travel | [8 empty] | total delay, except diversions (V hr) |  | 0
SPEED DELAY INPUT | [12 empty] | total vehicles canceled(V) |  | 0
|  |  |  | vehicle headway at gate (sec) |  | 3 | [6 empty] | total vehicles diverted (V) |  | 0
|  |  |  | dead time at gate when direction changes (sec) |  | 15 | [6 empty] | total decrease in demand (V) |  | 0
|  |  |  | allowable gate closed time (min.) | [8 empty] | % decrease in demand |  | 0%
DECREASE TO DEMAND INPUT | [12 empty] | delay per diverted vehicle (min) |  | 0
|  |  |  | canceled cars (with no delay) (%) | [8 empty] | total diversion delay (V hr) |  | 0
|  |  |  | canceled trucks (with no delay) (%) | [8 empty] | average delay, including diversions (min) |  | 0
|  |  |  | canceled cars (with delay) (%/min) | [8 empty] | total delay, including diversions (V hr) |  | 0
|  |  |  | canceled trucks (with delay) (%/min) | [8 empty] | user cost / design demand |  | 0
|  |  |  | diverted cars (with no delay) (%) | [8 empty] | delay cost / actual demand |  | 0
|  |  |  | diverted trucks (with no delay) (%) | 2 | [7 empty] | work zone method travel time (min.) |  | 0
|  |  |  | diverted cars (with delay) (%/min) | 2 | [7 empty] | speed delay (min.) |  | 0
|  |  |  | diverted trucks (with delay) (%/min) | [8 empty] | maximum capacity (V/hr) |  | 2400.04
OTHER USER COST INPUT | [5 empty] | cars | trucks | [5 empty] | gate delay at maximum capacity (min.) |  | 0
|  |  |  | other user cost per actual demand ($/V) |  | 0 | 0 | [5 empty] | maximum gate and speed delay (min.) |  | 0
|  |  |  | user cost per diversion ($/V) |  | 0 | 0 | [5 empty] | maximum backup delay (min.) |  | 0
Direction: |  |  | backup at start (V) |  |  | decrease | decrease |  | backup | backup |  | maximum | average |  | average | total
period | Flag | hist. | design | actual |  | to | to |  | eop | length |  | delay | backup |  | zone | period
|  | demand | demand | demand |  | cars | trucks |  |  | eop |  |  | delay |  | delay | delay
(hr) |  | (V/period) | (V/period) | (V/period) |  | (V/period) | (V/period) |  | (V) | (lane.mile) |  | (min) | (min) |  | (min) | (Vhr)
0 |  | 0 | 0
1 A |  | 0 | 0
2 A |  | 0 | 0
3 A |  | 0 | 0
4 A |  | 0 | 0
5 A |  | 0 | 0
6 A |  | 0 | 0
7 A |  | 0 | 0
8 A |  | 0 | 0
9 A |  | 0 | 0
10 A |  | 0 | 0
11 A |  | 0 | 0
12 P |  | 0 | 0
1 P |  | 0 | 0
2 P |  | 0 | 0
3 P |  | 0 | 0
4 P |  | 0 | 0
5 P |  | 0 | 0
6 P |  | 0 | 0
7 P |  | 0 | 0
8 P |  | 0 | 0
9 P |  | 0 | 0
10 P |  | 0 | 0
11 P |  | 0 | 0
TOT | 0 | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0
MAX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Cost View - Flagging Operation
|  |  | period length (min) | 60 |  | PROJECT INFORMATION | [5 empty] | REPORT INFORMATION
|  |  | annual traffic growth (%) |  |  | PROJECT | [5 empty] | REPORT | DETAILED USER COST REPORT
|  |  | years of growth |  |  | TITLE | [5 empty] | TITLE | USER COST VIEW
VEHICLE INPUT |  |  | cars | trucks |  |  | C.S. | 33081 |  |  |  |  | DIVISION
|  | design demand (%) | 100% |  |  |  | JOB # | [5 empty] | REPORT BY
|  | user cost per hour ($/V hr) | 11.41 | 11.41 |  |  | START DATE | 1997-04-30 |  |  |  |  | REPORT DATE
|  | user cost per mile, ($/V mi) | 0.3 | 1 |  |  |  |  | SUMMARY OUTPUT |  |  |  | traffic method
|  | user cost per cancellation, ($/V) | [10 empty] | total user cost |  | 0
METHOD INPUT | [5 empty] | METHOD 1 | [6 empty] | user cost of delays |  | 0
|  |  |  | method title | [8 empty] | user cost of decreases |  | 0
DISTANCE AND SPEED |  |  |  | (mi) (mph) |  | distance | speed | [5 empty] | maximum backup (V) |  | 0
|  | work zone |  | method travel | [8 empty] | maximum backup length (lane mi) |  | 0
|  |  |  | normal travel | [8 empty] | maximum delay (min.) |  | 0
|  | diversion |  | method travel | [8 empty] | average delay, except diversions (min) |  | 0
|  |  |  | normal travel | [8 empty] | total delay, except diversions (V hr) |  | 0
SPEED DELAY INPUT | [12 empty] | total vehicles canceled(V) |  | 0
|  |  |  | vehicle headway at gate (sec) |  | 3 | [6 empty] | total vehicles diverted (V) |  | 0
|  |  |  | dead time at gate when direction changes (sec) |  | 15 | [6 empty] | total decrease in demand (V) |  | 0
|  |  |  | allowable gate closed time (min.) | [8 empty] | % decrease in demand |  | 0%
DECREASE TO DEMAND INPUT | [12 empty] | delay per diverted vehicle (min) |  | 0
|  |  |  | canceled cars (with no delay) (%) | [8 empty] | total diversion delay (V hr) |  | 0
|  |  |  | canceled trucks (with no delay) (%) | [8 empty] | average delay, including diversions (min) |  | 0
|  |  |  | canceled cars (with delay) (%/min) | [8 empty] | total delay, including diversions (V hr) |  | 0
|  |  |  | canceled trucks (with delay) (%/min) | [8 empty] | user cost / design demand |  | 0
|  |  |  | diverted cars (with no delay) (%) | [8 empty] | delay cost / actual demand |  | 0
|  |  |  | diverted trucks (with no delay) (%) | 2 | [7 empty] | work zone method travel time (min.) |  | 0
|  |  |  | diverted cars (with delay) (%/min) | 2 | [7 empty] | speed delay (min.) |  | 0
|  |  |  | diverted trucks (with delay) (%/min) | [8 empty] | maximum capacity (V/hr) |  | 2400.04
OTHER USER COST INPUT | [5 empty] | cars | trucks | [5 empty] | gate delay at maximum capacity (min.) |  | 0
|  |  |  | other user cost per actual demand ($/V) |  | 0 | 0 | [5 empty] | maximum gate and speed delay (min.) |  | 0
|  |  |  | user cost per diversion ($/V) |  | 0 | 0 | [5 empty] | maximum backup delay (min.) |  | 0
Direction: |  |  | backup at start (V) |  |  | decrease | decrease |  | delay | delay |  | decrease | delay |  | user | user cost
period | Flag | design | cancel | divert |  | cost | cost |  | cost | cost |  | cost | cost |  | cost | / design
|  | demand | costs | costs |  | cars | trucks |  | cars | trucks | [5 empty] | demand
(hr) |  | (V/period) | ($) | ($) |  | ($) | ($) |  | ($) | ($) |  | ($) | ($) |  | ($) | ($/V)
0
1 A
2 A
3 A
4 A
5 A
6 A
7 A
8 A
9 A
10 A
11 A
12 P
1 P
2 P
3 P
4 P
5 P
6 P
7 P
8 P
9 P
10 P
11 P
TOT | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
MAX | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
MIN | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Combined View - Flagging Operation
|  |  | period length (min) | 60 |  | PROJECT INFORMATION | [5 empty] | REPORT INFORMATION
|  |  | annual traffic growth (%) |  |  | PROJECT | [5 empty] | REPORT | DETAILED USER COST REPORT
|  |  | years of growth |  |  | TITLE | [5 empty] | TITLE | COMBINED VIEW
VEHICLE INPUT |  |  | cars | trucks |  |  | C.S. | 33081 |  |  |  |  | DIVISION
|  | design demand (%) | 100% |  |  |  | JOB # | [5 empty] | REPORT BY
|  | user cost per hour ($/V hr) | 11.41 | 11.41 |  |  | START DATE | 1997-04-30 |  |  |  |  | REPORT DATE
|  | user cost per mile, ($/V mi) | 0.3 | 1 |  |  |  |  | SUMMARY OUTPUT |  |  |  | traffic method
|  | user cost per cancellation, ($/V) | [10 empty] | total user cost |  | 0
METHOD INPUT | [5 empty] | METHOD 1 | [6 empty] | user cost of delays |  | 0
|  |  |  | method title | [8 empty] | user cost of decreases |  | 0
DISTANCE AND SPEED |  |  |  | (mi) (mph) |  | distance | speed | [5 empty] | maximum backup (V) |  | 0
|  | work zone |  | method travel | [8 empty] | maximum backup length (lane mi) |  | 0
|  |  |  | normal travel | [8 empty] | maximum delay (min.) |  | 0
|  | diversion |  | method travel | [8 empty] | average delay, except diversions (min) |  | 0
|  |  |  | normal travel | [8 empty] | total delay, except diversions (V hr) |  | 0
SPEED DELAY INPUT | [12 empty] | total vehicles canceled(V) |  | 0
|  |  |  | vehicle headway at gate (sec) |  | 3 | [6 empty] | total vehicles diverted (V) |  | 0
|  |  |  | dead time at gate when direction changes (sec) |  | 15 | [6 empty] | total decrease in demand (V) |  | 0
|  |  |  | allowable gate closed time (min.) | [8 empty] | % decrease in demand |  | 0%
DECREASE TO DEMAND INPUT | [12 empty] | delay per diverted vehicle (min) |  | 0
|  |  |  | canceled cars (with no delay) (%) | [8 empty] | total diversion delay (V hr) |  | 0
|  |  |  | canceled trucks (with no delay) (%) | [8 empty] | average delay, including diversions (min) |  | 0
|  |  |  | canceled cars (with delay) (%/min) | [8 empty] | total delay, including diversions (V hr) |  | 0
|  |  |  | canceled trucks (with delay) (%/min) | [8 empty] | user cost / design demand |  | 0
|  |  |  | diverted cars (with no delay) (%) | [8 empty] | delay cost / actual demand |  | 0
|  |  |  | diverted trucks (with no delay) (%) | 2 | [7 empty] | work zone method travel time (min.) |  | 0
|  |  |  | diverted cars (with delay) (%/min) | 2 | [7 empty] | speed delay (min.) |  | 0
|  |  |  | diverted trucks (with delay) (%/min) | [8 empty] | maximum capacity (V/hr) |  | 2400.04
OTHER USER COST INPUT | [5 empty] | cars | trucks | [5 empty] | gate delay at maximum capacity (min.) |  | 0
|  |  |  | other user cost per actual demand ($/V) |  | 0 | 0 | [5 empty] | maximum gate and speed delay (min.) |  | 0
|  |  |  | user cost per diversion ($/V) |  | 0 | 0 | [5 empty] | maximum backup delay (min.) |  | 0
Direction: |  |  | backup at start (V) |  |  | backup | maximum |  | average | average |  | decrease | delay |  | user | delay cost
period | Flag | actual | total | total |  | eop | delay |  | backup | zone |  | cost | cost |  | cost | / actual
|  | demand | decrease | delay |  |  |  |  | delay | delay | [5 empty] | demand
(hr) |  | (V/period) | (V/period) | (V hr) |  | (V) | (min) |  | (min) | (min) |  | ($) | ($) |  | ($) | ($/V)
0
1 A
2 A
3 A
4 A
5 A
6 A
7 A
8 A
9 A
10 A
11 A
12 P
1 P
2 P
3 P
4 P
5 P
6 P
7 P
8 P
9 P
10 P
11 P
TOT | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
MAX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General and Default Input, with Relevant Output
Speed delay exponent |  |  |  | ES |  |  | 2 | [5 empty] | maximum backup (V)
Vehicle length in backup (ft) |  |  |  | LB |  |  | 30 | [5 empty] | maximum backup length (lane mi)
Allowed difference in Tdel.V (min) |  |  |  | edel.allowed |  |  | 0.1 | [5 empty] | total vehicles canceled(V)
Allowed diff as % of max design demand | [6 empty] | 0.2% | [5 empty] | total vehicles diverted (V)
Maximum design demand (V) | [6 empty] | 0 | [5 empty] | total decrease in demand (V)
Allowed difference in Da calculation (V) |  |  |  | eD.allowed |  |  | 0 | [5 empty] | % decrease in demand
Average difference in Tdel.V(min) |  |  |  | edel.avg | [8 empty] | maximum vehicle delay (min.)
Average difference in Da (min) |  |  |  | eD.avg | [8 empty] | total delay (V hr)
Allowed number of interations |  |  |  | AllowedCycles |  |  | 20 | [5 empty] | user cost / design demand
Iterations at which to check converge |  |  |  | ReportCycles |  |  | 1 | [5 empty] | delay cost / actual demand
Converge method (1=intercept, 2=combo, 3=interpolate) |  |  |  | ConvergeMethod |  |  | 1 | [5 empty] | user cost of decreases
Total number of iterative cycles |  |  |  | TotalCycles | [8 empty] | user cost of delays
Max cycles to converge |  |  |  | MaxCycles |  |  | 0 | [5 empty] | total user cost
Period of max cycles to converge |  |  |  | MaxCyclesI |  |  | 6
Max periods of backup |  |  |  | MaxPeriods | 2 |  | 0
Period of max periods of backup |  |  |  | MaxPeriodsI |  |  | 15
Default Capacity after Flagging (VPH, both directions) |  |  |  | CPostFlagDefault |  |  | 2400
|  | OUTPUT | [6 empty] | Method
[6 empty] | total user cost | 0 |  | Number
[6 empty] | user cost of delays | 0 |  | 4
[6 empty] | user cost of decreases | 0 |  | Direction
[6 empty] | maximum backup (V) | 0 |  | Number
[6 empty] | maximum backup length (lane mi) | 0 |  | 1
[6 empty] | maximum delay (min.) | 0
[6 empty] | average delay, except diversions (min) | 0
[6 empty] | total delay, except diversions (V hr) | 0 |  | Times: |  |  |  | Delta (sec)
[6 empty] | total vehicles canceled(V) | 0 |  | Start | Times 1 |  | 11:40
[6 empty] | total vehicles diverted (V) | 0 |  | After input | Times 2 |  | 11:40 | 2.3148
[6 empty] | total decrease in demand (V) | 0 |  | Calc Overall | Times 3 |  | 11:40 | 0
[6 empty] | % decrease in demand | 0% |  | DelayDemand | Times 4 |  | 11:40 | 0
[6 empty] | delay per diverted vehicle (min) | 0 |  | Calc views | Times 5 |  | 11:40 | 1.1574
[6 empty] | total diversion delay (V hr) | 0 |  | Checksum | Times 6 |  | 11:40 | 1.1574
[6 empty] | average delay, including diversions (min) | 0 |  | Validity | Times 7 |  | 11:40 | 0
[6 empty] | total delay, including diversions (V hr) | 0 |  |  | Overall delta (sec)= |  |  | 4.6296
[6 empty] | user cost / design demand | 0
[6 empty] | delay cost / actual demand | 0
[6 empty] | work zone method travel time (min.) | 0
[6 empty] | speed delay (min.) | 0
[6 empty] | maximum capacity (V/hr) | 2400.04
[6 empty] | gate delay at maximum capacity (min.) | 0
[6 empty] | maximum gate and speed delay (min.) | 0 |  | T.del.Z.max
[6 empty] | maximum backup delay (min.) | 0
Seed: | 0.0137
Interval: | 1.0023 | SummaryInputGeneral |  |  |  | SummaryInputMethod_I |  |  | SummaryInputMethod_I |  |  | SummaryInputMethod_I |  |  | SummaryInputMethod_I
1 | 1.0183 | 61.1002 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
2 | 1.0344 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 1.0505 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 1.0667 | 1.0667 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 1.0829 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
6 | 1.0991 | 34.8737 |  |  |  | 3.2972 | 0 |  | 3.2972 | 0 |  | 3.2972 | 0 |  | 3.2972 | 0
7 | 1.1153 | 2.0857 |  |  |  | 16.73 | 0 |  | 16.73 | 0 |  | 16.73 | 0 |  | 16.73 | 0
8 | 1.1316 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
9 | 1.148 | 1.148 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
10 | 1.1643 | 20.9348 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
11 | 1.1807 | 0.67893 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
12 | 1.1972 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
13 | 1.2137 | 121.8879 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
14 | 1.2302 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
15 | 1.2468 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
16 | 1.2634 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
17 | 1.28 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
18 | 1.2967 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
19 | 1.3134 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
20 | 1.3301 |  |  |  |  | 20.0273 | 0 |  | 20.0273 | 0 |  | 20.0273 | 0 |  | 20.0273 | 0
21 | 1.3469 |  |  |  |  | 20.0273 | 20.0273 |  | 20.0273 | 20.0273 |  | 20.0273 | 20.0273 |  | 20.0273 | 20.0273
22 | 1.3638
23 | 1.3806
24 | 1.3975
1.4145
|  | SummaryDemandHist_j |  |  |  | SummaryCapacity_ij |  |  | SummaryCapacity_ij |  |  | SummaryCapacity_ij |  |  | SummaryCapacity_ij
| 1 | 0 | 0 |  |  | 1.0183 |  |  | 1.0183 |  |  | 1.0183 |  |  | 1.0183
| 2 | 0 | 0 |  |  | 1.0344 |  |  | 1.0344 |  |  | 1.0344 |  |  | 1.0344
| 3 | 0 | 0 |  |  | 1.0505 |  |  | 1.0505 |  |  | 1.0505 |  |  | 1.0505
| 4 | 0 | 0 |  |  | 1.0667 |  |  | 1.0667 |  |  | 1.0667 |  |  | 1.0667
| 5 | 0 | 0 |  |  | 1.0829 |  |  | 1.0829 |  |  | 1.0829 |  |  | 1.0829
| 6 | 0 | 0 |  |  | 1.0991 |  |  | 1.0991 |  |  | 1.0991 |  |  | 1.0991
| 7 | 0 | 0 |  |  | 1.1153 |  |  | 1.1153 |  |  | 1.1153 |  |  | 1.1153
| 8 | 0 | 0 |  |  | 1.1316 |  |  | 1.1316 |  |  | 1.1316 |  |  | 1.1316
| 9 | 0 | 0 |  |  | 1.148 |  |  | 1.148 |  |  | 1.148 |  |  | 1.148
| 10 | 0 | 0 |  |  | 1.1643 |  |  | 1.1643 |  |  | 1.1643 |  |  | 1.1643
| 11 | 0 | 0 |  |  | 1.1807 |  |  | 1.1807 |  |  | 1.1807 |  |  | 1.1807
| 12 | 0 | 0 |  |  | 1.1972 |  |  | 1.1972 |  |  | 1.1972 |  |  | 1.1972
| 13 | 0 | 0 |  |  | 1.2137 |  |  | 1.2137 |  |  | 1.2137 |  |  | 1.2137
| 14 | 0 | 0 |  |  | 1.2302 |  |  | 1.2302 |  |  | 1.2302 |  |  | 1.2302
| 15 | 0 | 0 |  |  | 1.2468 |  |  | 1.2468 |  |  | 1.2468 |  |  | 1.2468
| 16 | 0 | 0 |  |  | 1.2634 |  |  | 1.2634 |  |  | 1.2634 |  |  | 1.2634
| 17 | 0 | 0 |  |  | 1.28 |  |  | 1.28 |  |  | 1.28 |  |  | 1.28
| 18 | 0 | 0 |  |  | 1.2967 |  |  | 1.2967 |  |  | 1.2967 |  |  | 1.2967
| 19 | 0 | 0 |  |  | 1.3134 |  |  | 1.3134 |  |  | 1.3134 |  |  | 1.3134
| 20 | 0 | 0 |  |  | 1.3301 |  |  | 1.3301 |  |  | 1.3301 |  |  | 1.3301
| 21 | 0 | 0 |  |  | 1.3469 |  |  | 1.3469 |  |  | 1.3469 |  |  | 1.3469
| 22 | 0 | 0 |  |  | 1.3638 |  |  | 1.3638 |  |  | 1.3638 |  |  | 1.3638
| 23 | 0 | 0 |  |  | 1.3806 |  |  | 1.3806 |  |  | 1.3806 |  |  | 1.3806
| 24 | 0 | 0 |  |  | 1.3975 |  |  | 1.3975 |  |  | 1.3975 |  |  | 1.3975
|  | 0 | 0 |  |  | 28.9522 | 0 |  | 28.9522 | 0 |  | 28.9522 | 0 |  | 28.9522 | 0
[6 empty] | SummaryOutput_ij |  |  | SummaryOutput_ij |  |  | SummaryOutput_ij |  |  | SummaryOutput_ij
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Checksums: |  |  | Method: |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4
|  |  | Direction: |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
Auto Validity Status |  |  | SummaryInputGeneral: |  |  | 121.8879 |  |  | 121.8879 |  |  | 121.8879 |  |  | 121.8879
ON |  |  | SummaryInputMethod_I |  |  | 20.0273 |  |  | 20.0273 |  |  | 20.0273 |  |  | 20.0273
|  |  | SummaryCapacity_ij |  |  | 28.9522 |  |  | 28.9522 |  |  | 28.9522 |  |  | 28.9522
Print Validity Status |  |  | SummaryDemandHist_1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
ON |  |  | SummaryDemandHist_2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | SummaryOutput_ij |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Now Valid Status |  |  | Total Current: |  |  | 170.8673 |  |  | 170.8673 |  |  | 170.8673 |  |  | 170.8673
OK |  |  | Total Saved (from calc) |  |  | 139.5894 |  |  | 139.5894 |  |  | 139.5894 |  |  | 139.5894
|  |  | Difference: |  |  | -31.278 |  |  | -31.278 |  |  | -31.278 |  |  | -31.278
Range = Bottom |  |  | Validity: |  |  | NOT VALID |  |  | NOT VALID |  |  | NOT VALID |  |  | NOT VALID
Note on H118: Dcan.p.cars.wo.del.C.threshold
Note on I405: R. I. Carr: Maximum difference used in testing convergence during iteration. (Default = 0.1)
Note on I406: This scales value of allowed difference in actual demand. (Default = 0.20%)
Note on I408: R. I. Carr: Maximum difference used in testing convergence during iteration.
Note on I409: Compare this to allowed difference above.
Note on I410: Compare this to allowed difference above.
Note on I411: Sets maximum iterations allowed. Error message if does not converge. (Default = 20)
Note on I412: Offset from allowed number of iterations at which error messages start reporting values of trial delay and actual demand values. (Default = 1)
Note on I413: This sets convergence method. (Default=1)
Note on I414: Reports number of iterations. Divide by 24 periods to calculate average iterations per period.
Note on I415: Reports the maximum number of iterations that a period required for delay and demand to converge.
Note on I416: Reports the period (of 24 periods) that had the maximum cycles to converge.
Note on I417: Maximum number of periods that were required for a backup to dissipate.
Note on I418: Period (of 24) at which backup caused Max periods of backup.
Compute
Compute
Compute
Compute
Overall
Update
Update
Print:
ON
Auto:
ON
Now:
OK
Print:
Summary
Overall
All
This View
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Traffic
Go To: Summary
Traffic
User Cost
Combined
Overall
User Cost
Go To: Summary
Traffic
User Cost
Combined
Overall
Combo
Print:
Summary
Overall
All
This View
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Summary
Print:
Summary
Overall
All
This View
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Print:
Summary
Overall
All
This View
Setup
Print:
Summary
Overall
All
This View
Setup
Print:
Summary
Overall
All
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Print:
Summary
Overall
All
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Print:
Summary
Overall
All
This View
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Print:
Summary
Overall
All
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Print:
Summary
Overall
All
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Overall
Print:
Summary
Overall
All
This View
Go To: Summary
Traffic
User Cost
Combined
Overall
Setup
Copy This Sheet
You can copy these values into Impact Sheet.
Paste Values
Paste Values

## ADT
CS:
JN:
PROJECT DESCRIP: | [7 empty] | 1 | Urban/Rural
[8 empty] | 2 | Rural
[8 empty] | 3 | Urban
[8 empty] | 4 | Recreational Collector
[8 empty] | 5 | Recreational Corridor
[8 empty] | 6 | Rural/Recreational
|  | AVG. ADT= | 25377 |  |  | PATTERN= | 2 | 7 | Urban Area Limit
|  | Corrected ADT (avg. weekday)= |  |  | 26136.6621 |  |  | 8 | Recreational
|  | Corrected ADT (avg. weekend)= |  |  | 23657.4026 | [5 empty] | Worst case
[9 empty] | wk-end |  | HRLY'S
|  | 7 DAY %'s | 7day hrly |  | wk-day %'s | wk-day hrly |  | wk-end %'s | 2 day hrly |  | use for Fri.
TIME PER. |  | (INPUT) | volumes |  | (INPUT) | volumes |  | (INPUT) | volumes |  | & Sun. vol's
12-1 |  | 0.017 | 215.7045 |  | 0.017 | 222.1616 |  | 0.017 | 201.0879 |  | 222.1616
1-2 |  | 0.014 | 177.639 |  | 0.014 | 182.9566 |  | 0.014 | 165.6018 |  | 182.9566
2-3 |  | 0.013 | 164.9505 |  | 0.013 | 169.8883 |  | 0.013 | 153.7731 |  | 169.8883
3-4 |  | 0.013 | 164.9505 |  | 0.013 | 169.8883 |  | 0.013 | 153.7731 |  | 169.8883
4-5 |  | 0.014 | 177.639 |  | 0.014 | 182.9566 |  | 0.014 | 165.6018 |  | 182.9566
5-6 |  | 0.021 | 266.4585 |  | 0.021 | 274.435 |  | 0.021 | 248.4027 |  | 274.435
6-7 |  | 0.037 | 469.4745 |  | 0.037 | 483.5282 |  | 0.037 | 437.6619 |  | 483.5282
7-8 |  | 0.049 | 621.7365 |  | 0.049 | 640.3482 |  | 0.049 | 579.6064 |  | 640.3482
8-9 |  | 0.049 | 621.7365 |  | 0.049 | 640.3482 |  | 0.049 | 579.6064 |  | 640.3482
9-10 |  | 0.052 | 659.802 |  | 0.052 | 679.5532 |  | 0.052 | 615.0925 |  | 679.5532
10-11 |  | 0.055 | 697.8675 |  | 0.055 | 718.7582 |  | 0.055 | 650.5786 |  | 718.7582
11-12 |  | 0.058 | 735.933 |  | 0.058 | 757.9632 |  | 0.058 | 686.0647 |  | 757.9632
12-1 |  | 0.057 | 723.2445 |  | 0.057 | 744.8949 |  | 0.057 | 674.236 |  | 744.8949
1-2 |  | 0.059 | 748.6215 |  | 0.059 | 771.0315 |  | 0.059 | 697.8934 |  | 771.0315
2-3 |  | 0.063 | 799.3755 |  | 0.063 | 823.3049 |  | 0.063 | 745.2082 |  | 823.3049
3-4 |  | 0.069 | 875.5065 |  | 0.069 | 901.7148 |  | 0.069 | 816.1804 |  | 901.7148
4-5 |  | 0.072 | 913.572 |  | 0.072 | 940.9198 |  | 0.072 | 851.6665 |  | 940.9198
5-6 |  | 0.066 | 837.441 |  | 0.066 | 862.5098 |  | 0.066 | 780.6943 |  | 862.5098
6-7 |  | 0.053 | 672.4905 |  | 0.053 | 692.6215 |  | 0.053 | 626.9212 |  | 692.6215
7-8 |  | 0.044 | 558.294 |  | 0.044 | 575.0066 |  | 0.044 | 520.4629 |  | 575.0066
8-9 |  | 0.038 | 482.163 |  | 0.038 | 496.5966 |  | 0.038 | 449.4906 |  | 496.5966
9-10 |  | 0.034 | 431.409 |  | 0.034 | 444.3233 |  | 0.034 | 402.1758 |  | 444.3233
10-11 |  | 0.029 | 367.9665 |  | 0.029 | 378.9816 |  | 0.029 | 343.0323 |  | 378.9816
11-12 |  | 0.024 | 304.524 |  | 0.024 | 313.6399 |  | 0.024 | 283.8888 |  | 313.6399
|  | 1 | 12688.5 |  | 1 | 13068.331 |  |  | 11828.7013 |  | 13068.331
|  | AVG ADT= | 25377
|  | (INPUT) | PATTERN 1 - URBAN/RURAL |  |  |  |  | PATTERN 2 - RURAL |  |  |  | PATTERN 3 - URBAN |  |  |  | PATTERN 4 - RECREATIONAL COLLECTOR |  |  |  | PATTERN 5 - RECREATIONAL CORRIDOR |  |  |  |  | PATTERN 6 - RURAL/RECREATIONAL |  |  |  | PATTERN 7 - URBAN AREA LIMIT |  |  |  | PATTERN 8 - RECREATIONAL
2014 DOW Factors for Patterns | JAN | 1 | 1.1341 | 1.1341 | 1.6831 | 1.6831 |  | 1.2833 | 1.2833 | 1.6062 | 1.6062 | 1.0322 | 1.0322 | 1.7854 | 1.7854 | 1.4312 | 1.4312 | 1.5009 | 1.5009 |  | 1.5962 | 1.5962 | 1.5441 | 1.5441 | 1.2046 | 1.2046 | 1.5838 | 1.5838 | 1.0702 | 1.0702 | 1.5601 | 1.5601 | 1.5223 | 1.5223 | 1.7673 | 1.7673
| FEB | 1 | 0.99156 | 0.99156 | 1.4718 | 1.4718 |  | 1.1116 | 1.1116 | 1.3977 | 1.3977 | 0.90576 | 0.90576 | 1.5999 | 1.5999 | 1.2839 | 1.2839 | 1.2967 | 1.2967 |  | 1.4416 | 1.4416 | 1.3298 | 1.3298 | 1.0985 | 1.0985 | 1.3574 | 1.3574 | 0.9382 | 0.9382 | 1.4136 | 1.4136 | 1.325 | 1.325 | 1.4469 | 1.4469
| MARCH | 1 | 0.95196 | 0.95196 | 1.3072 | 1.3072 |  | 1.0308 | 1.0308 | 1.1773 | 1.1773 | 0.87324 | 0.87324 | 1.444 | 1.444 | 1.2394 | 1.2394 | 1.1972 | 1.1972 |  | 1.4224 | 1.4224 | 1.2999 | 1.2999 | 1.0766 | 1.0766 | 1.3177 | 1.3177 | 0.89876 | 0.89876 | 1.2652 | 1.2652 | 1.2678 | 1.2678 | 1.3562 | 1.3562
| APRIL | 1 | 0.90664 | 0.90664 | 1.1857 | 1.1857 |  | 0.95736 | 0.95736 | 1.0395 | 1.0395 | 0.83562 | 0.83562 | 1.3197 | 1.3197 | 1.1257 | 1.1257 | 1.043 | 1.043 |  | 1.2683 | 1.2683 | 1.18 | 1.18 | 1.0624 | 1.0624 | 1.2643 | 1.2643 | 0.883 | 0.883 | 1.2113 | 1.2113 | 1.1449 | 1.1449 | 1.1868 | 1.1868
| MAY | 1 | 0.86006 | 0.86006 | 1.0962 | 1.0962 |  | 0.90122 | 0.90122 | 0.97525 | 0.97525 | 0.81346 | 0.81346 | 1.2378 | 1.2378 | 0.9056 | 0.9056 | 0.8297 | 0.8297 |  | 0.87012 | 0.87012 | 0.79445 | 0.79445 | 0.89086 | 0.89086 | 1.0333 | 1.0333 | 0.86868 | 0.86868 | 1.1633 | 1.1633 | 0.84958 | 0.84958 | 0.77235 | 0.77235
| JUNE | 1 | 0.8453 | 0.8453 | 1.0476 | 1.0476 |  | 0.8613 | 0.8613 | 0.8837 | 0.8837 | 0.79682 | 0.79682 | 1.2367 | 1.2367 | 0.846 | 0.846 | 0.7004 | 0.7004 |  | 0.76102 | 0.76102 | 0.60105 | 0.60105 | 0.8136 | 0.8136 | 0.93 | 0.93 | 0.85326 | 0.85326 | 1.1497 | 1.1497 | 0.7679 | 0.7679 | 0.69785 | 0.69785
| JULY | 1 | 0.8452 | 0.8452 | 1.0332 | 1.0332 |  | 0.82702 | 0.82702 | 0.84345 | 0.84345 | 0.81734 | 0.81734 | 1.2884 | 1.2884 | 0.70028 | 0.70028 | 0.55385 | 0.55385 |  | 0.54552 | 0.54552 | 0.415 | 0.415 | 0.75212 | 0.75212 | 0.80255 | 0.80255 | 0.86754 | 0.86754 | 1.2007 | 1.2007 | 0.6072 | 0.6072 | 0.52015 | 0.52015
| AUGUST | 1 | 0.83478 | 0.83478 | 1.0108 | 1.0108 |  | 0.826 | 0.826 | 0.8277 | 0.8277 | 0.7959 | 0.7959 | 1.2408 | 1.2408 | 0.71732 | 0.71732 | 0.57655 | 0.57655 |  | 0.5592 | 0.5592 | 0.42885 | 0.42885 | 0.7386 | 0.7386 | 0.81975 | 0.81975 | 0.87062 | 0.87062 | 1.1609 | 1.1609 | 0.60984 | 0.60984 | 0.51885 | 0.51885
| SEPT | 1 | 0.8741 | 0.8741 | 1.0756 | 1.0756 |  | 0.90938 | 0.90938 | 0.93975 | 0.93975 | 0.80342 | 0.80342 | 1.241 | 1.241 | 0.88232 | 0.88232 | 0.76995 | 0.76995 |  | 0.75894 | 0.75894 | 0.6481 | 0.6481 | 0.82136 | 0.82136 | 0.92635 | 0.92635 | 0.8657 | 0.8657 | 1.17 | 1.17 | 0.7425 | 0.7425 | 0.6827 | 0.6827
| OCT | 1 | 0.86864 | 0.86864 | 1.0879 | 1.0879 |  | 0.92178 | 0.92178 | 0.95705 | 0.95705 | 0.79562 | 0.79562 | 1.2485 | 1.2485 | 0.93486 | 0.93486 | 0.75365 | 0.75365 |  | 0.86752 | 0.86752 | 0.66655 | 0.66655 | 0.87326 | 0.87326 | 0.96295 | 0.96295 | 0.85506 | 0.85506 | 1.1684 | 1.1684 | 0.84366 | 0.84366 | 0.7554 | 0.7554
| NOV | 1 | 0.93694 | 0.93694 | 1.2333 | 1.2333 |  | 0.99676 | 0.99676 | 1.078 | 1.078 | 0.86032 | 0.86032 | 1.3634 | 1.3634 | 1.0559 | 1.0559 | 1.0088 | 1.0088 |  | 1.0284 | 1.0284 | 0.9602 | 0.9602 | 1.0245 | 1.0245 | 1.1925 | 1.1925 | 0.9152 | 0.9152 | 1.27 | 1.27 | 1.1043 | 1.1043 | 1.0762 | 1.0762
| DEC | 1 | 0.95872 | 0.95872 | 1.2476 | 1.2476 |  | 1.0248 | 1.0248 | 1.1465 | 1.1465 | 0.91102 | 0.91102 | 1.3925 | 1.3925 | 1.1414 | 1.1414 | 1.1099 | 1.1099 |  | 1.2612 | 1.2612 | 1.1809 | 1.1809 | 1.054 | 1.054 | 1.2837 | 1.2837 | 0.9248 | 0.9248 | 1.2391 | 1.2391 | 1.1925 | 1.1925 | 1.2752 | 1.2752
|  | 12 |  | 11.008 |  | 14.4801 |  |  | 11.6512 |  | 12.8722 | 10.2407 |  | 16.3981 |  | 12.2639 |  | 11.3404 |  |  | 12.3803 |  | 11.0489 |  | 11.4104 |  | 13.4743 |  | 10.811 |  | 14.9725 |  | 11.9775 |  | 12.0561
|  |  |  | 0.91734 |  | 1.2067 |  |  | 0.97093 |  | 1.0727 | 0.8534 |  | 1.3665 |  | 1.022 |  | 0.94503 |  |  | 1.0317 |  | 0.92075 |  | 0.95086 |  | 1.1229 |  | 0.90092 |  | 1.2477 |  | 0.99813 |  | 1.0047
|  |  | COR ADT= | 27663.7803 | COR ADT= | 21030.5904 |  | COR ADT= | 26136.6621 | COR ADT= | 23657.4026 | 29736.5229 | =COR ADT | 18570.6881 | =COR ADT | 24830.967 | =COR ADT | 26853.0211 | =COR ADT |  | 24597.4256 | =COR ADT | 27561.352 | =COR ADT | 26688.3779 | =COR ADT | 22600.3577 | =COR ADT | 28167.925 | =COR ADT | 20338.888 | =COR ADT | 25424.6713 | =COR ADT | 25258.9146 | =COR ADT
|  |  | WEEKDAY |  | WEEKEND |  |  | WEEKDAY |  | WEEKEND |  |  | WEEKDAY |  | WEEKEND |  | WEEKDAY |  | WEEKEND |  |  | WEEKDAY |  | WEEKEND |  | WEEKDAY |  | WEEKEND |  | WEEKDAY |  | WEEKEND |  | WEEKDAY |  | WEEKEND
PennDOT AADT Distribution (hourly percentages)
| Interstate |  | Principal Arterial |  | Minor Arterial
TIME PER. | Urban | Rural | Urban | Rural | Urban | Rural
12-1 | 0.013 | 0.017 | 0.009 | 0.009 | 0.008 | 0.007
1-2 | 0.009 | 0.014 | 0.005 | 0.005 | 0.004 | 0.004
2-3 | 0.008 | 0.013 | 0.004 | 0.005 | 0.003 | 0.003
3-4 | 0.008 | 0.013 | 0.004 | 0.005 | 0.003 | 0.004
4-5 | 0.011 | 0.014 | 0.006 | 0.009 | 0.004 | 0.008
5-6 | 0.021 | 0.021 | 0.018 | 0.023 | 0.013 | 0.022
6-7 | 0.047 | 0.037 | 0.044 | 0.049 | 0.04 | 0.045
7-8 | 0.064 | 0.049 | 0.062 | 0.062 | 0.064 | 0.055
8-9 | 0.056 | 0.049 | 0.057 | 0.055 | 0.057 | 0.053
9-10 | 0.051 | 0.052 | 0.051 | 0.053 | 0.048 | 0.054
10-11 | 0.052 | 0.055 | 0.052 | 0.054 | 0.049 | 0.058
11-12 | 0.054 | 0.058 | 0.056 | 0.056 | 0.055 | 0.06
12-1 | 0.055 | 0.057 | 0.06 | 0.057 | 0.06 | 0.062
1-2 | 0.055 | 0.059 | 0.059 | 0.059 | 0.057 | 0.064
2-3 | 0.061 | 0.063 | 0.064 | 0.066 | 0.063 | 0.072
3-4 | 0.073 | 0.069 | 0.074 | 0.077 | 0.076 | 0.081
4-5 | 0.078 | 0.072 | 0.078 | 0.08 | 0.083 | 0.08
5-6 | 0.072 | 0.066 | 0.075 | 0.074 | 0.08 | 0.071
6-7 | 0.054 | 0.053 | 0.059 | 0.055 | 0.062 | 0.054
7-8 | 0.043 | 0.044 | 0.048 | 0.043 | 0.051 | 0.044
8-9 | 0.037 | 0.038 | 0.04 | 0.036 | 0.043 | 0.036
9-10 | 0.032 | 0.034 | 0.033 | 0.03 | 0.034 | 0.029
10-11 | 0.026 | 0.029 | 0.024 | 0.023 | 0.024 | 0.021
11-12 | 0.02 | 0.024 | 0.017 | 0.015 | 0.016 | 0.014
Note on C14: KromB: See way below for PennDOT table if nothing provided.
Note on D9: KromB: Input AADT for this project
Note on F14: KromB: See way below for PennDOT table if week day %'s not provided.
Note on I14: KromB: If weekend %'s not provided, use weekday %'s. Otherwise, see way below for PennDOT table.

## flag input
PROJECT INPUT AND DOCUMENTATION |  | Project:
FLAGGING OPERATION |  | By:
Other:
METHOD INPUT | METHOD #
method title
VEHICLE INPUT | cars | trucks
design demand (%)
user cost per hour ($/V hr) | 10.79 | 10.79 | default
user cost per mile, ($/V mi) | 0.3 | 1 | default
user cost per cancellation, ($/V)
ROUTE TITLES | Standard
DISTANCE AND SPEED INPUT | distance | speed
work zone method travel
work zone normal travel
diversion method travel
diversion normal travel
FLAG OPERATION INPUT
vehicle headway at gate (sec) | 3 |  | default
dead time at gate when direction changes (sec) | 15 |  | default
allowable gate closed time (min.)
WORK ZONE TRAVEL
method travel time (min)
normal travel time (min)
speed delay (min)
gate delay at D~0 (min)
gate delay at maximum capacity (min)
gate and speed delay at D~0 (min)
gate+speed delay at max capacity (min)
maximum capacity (V/hr)
ZONE USER COST | cars | trucks
gate+speed delay user cost at D~0
gate+speed delay user cost at max capacity
DIVERSION TRAVEL
method travel time (min)
normal travel time (min)
diversion delay (min)
extra diversion travel distance (mi)
DIVERSION USER COST | cars | trucks
diversion delay user cost
diversion distance user cost
diversion user cost
backup delay balance (min)
DECREASE TO DEMAND INPUT
canceled cars (with no delay) (%)
canceled trucks (with no delay) (%)
canceled cars (with delay) (%/min)
canceled trucks (with delay) (%/min)
diverted cars (with no delay) (%)
diverted trucks (with no delay) (%)
diverted cars (with delay) (%/min)
diverted trucks (with delay) (%/min)
OTHER USER COST INPUT | cars | trucks
other user cost per vehicle ($/V) | 0 | 0 | default
user cost per diversion ($/V)
CAPACITY INPUT | normal
total capacity both ways (V/hr) | 2400 |  | default
Note on B44: Dcan.p.cars.wo.del.C.threshold
General Comments:
Copy This Sheet
4
0
0
1
1
1
1
1
2
3
2
5
5
5
5
6
6
6
6
1

## flag routes
FLAG ROUTE CALCULATIONS |  |  |  |  | Project:
By:
Other:
ROUTE USER COSTS
VEHICLE INPUT |  |  | cars | trucks
|  | user cost per hour ($/V hr) | 10.79 | 10.79
|  | user cost per mile, ($/V mi) | 0.3 | 1
ROUTE TITLES
DISTANCE AND SPEED INPUT |  |  |  | (mi) (mph) | distance | speed | distance | speed | distance | speed | distance | speed
|  | work zone |  | method travel
normal travel
|  | diversion |  | method travel
normal travel
FLAG OPERATION INPUT
vehicle headway at gate (sec)
dead time at gate when direction changes (sec)
allowable gate closed time (min.)
WORK ZONE TRAVEL
method travel time (min)
normal travel time (min)
speed delay (min)
minimum gate delay (min)
maximum gate delay (min)
minimum gate and speed delay (min)
maximum gate and speed delay (min)
maximum capacity (V/hr)
ZONE USER COST |  |  |  |  | cars | trucks | cars | trucks | cars | trucks | cars | trucks
minimum gate and speed delay user cost
maximum gate and speed delay user cost
DIVERSION TRAVEL
| diversion |  |  | method travel time (min)
| diversion |  |  | normal travel time (min)
diversion delay (min)
extra diversion travel distance (mi)
DIVERSION USER COST |  |  |  |  | cars | trucks | cars | trucks | cars | trucks | cars | trucks
diversion delay user cost
diversion distance user cost
diversion user cost
backup delay balance (min)
ROUTE DISTANCE, SPEED, AND TIME | [5 empty] | Route Title:
Normal Travel | [6 empty] | Method Travel
Input |  |  |  | Calculated Values |  |  | Input |  |  |  | Calculated Values
Route/ Road Name | % that Take Route/ Road | Distance (mi) | Speed (mph) | Travel Time (min) | Weighted Distance (mi) | Weighted Travel Time (min) | Route/ Road Name | % that Take Route/ Road | Distance (mi) | Speed (mph) | Travel Time (min) | Weighted Distance (mi) | Weighted Travel Time (min)
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Totals | 0 |  |  |  | 0 | 0 | Totals | 0 |  |  |  | 0 | 0
Averages |  | 0 | #DIV/0! | #DIV/0! |  |  | Averages |  | 0 | #DIV/0! | #DIV/0!
[7 empty] | Differences |  | 0 | #DIV/0! | #DIV/0!
Copy This Sheet

## impact
IMPACT SUMMARY SHEET
SUMMARY SHEET INPUT Project:
By:
Other:
TRAFFIC SUMMARY INPUT % closed |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
traffic method
direction
total user cost ($)
user cost of delays ($)
user cost of decreases ($)
maximum backup (V)
maximum backup length (lane mi)
maximum delay (min.)
average delay (min)
total delay, except diversions (V hr)
total vehicles canceled (V)
total vehicles diverted (V)
total decrease in demand (V)
% decrease in demand
delay per diverted vehicle (min)
total diversion delay (V hr)
average delay, including diversions (min)
total delay, including diversions (V hr)
user cost / design demand ($/V)
delay cost / actual demand ($/V)
CONSTRUCTION SUMMARY INPUT
lane-closed hours per day (hr/day)
lane-closed days (day)
labor cost ($)
project cost ($)
SUMMARY OF IMPACTS
By:
Other:
USER COST, DAILY | traffic method
total user cost, daily ($)
user cost of delays, daily ($)
user cost of decreases , daily ($)
total delay, except diversions, daily (V hr)
total vehicles canceled, daily (V)
total vehicles diverted, daily (V)
total decrease in demand, daily (V)
total diversion delay, daily (V hr)
total delay, including diversions, daily (V hr)
USER COST, TOTAL
total user cost ($)
user cost of delays ($)
user cost of decreases ($)
maximum backup (V)
maximum backup length (lane mi)
maximum delay (min.)
average delay (min)
total delay, except diversions (V hr)
total vehicles canceled (V)
total vehicles diverted (V)
total decrease in demand (V)
% decrease in demand
average delay per diverted vehicle (min)
total diversion delay (V hr)
average delay, including diversions (min)
total delay, including diversions (V hr)
average user cost / design demand ($/V)
average delay cost / actual demand ($/V)
CONSTRUCTION COST | method
lane-closed hours per day (hr/day)
lane-closed days (day)
labor cost ($)
project cost ($)
TOTAL PROJECT COST
Note on B5: A lane in one direction closed each day = 50% A lane in both directions closed each day = 100%
Copy This Sheet
Copy This Sheet
Do not change or copy in summaries below this area
Do not change these areas or copy into these areas.
You can add comments between table above and this box.
Do not change these areas or copy into these areas.
Do not change or copy in summaries below this area
PASTE VALUES only from Summary View of Traffic Sheet.
Use DELETE to undo.
PASTE VALUES only from Construction Sheet. Use DELETE to undo.
Do not change these areas or copy into these areas.
Paste Values
Paste Values
Paste Values
Paste Values
Print Summary of Impacts for 4 Methods, Vertical
Print Summary of Impacts for 7 Methods, Horizontal

## daily
Daily Cost Sheet Tables |  |  |  | Note: This Daily Sheet now includes Project Cost View.
User Cost View
Period Cost View |  |  | Period Cost Input
Detailed Cost View |  |  | Fraction = P/U = |  | 100% | [6 empty] | Daily Cost View | [6 empty] | Project: | [7 empty] | Method:
Daily Cost View |  |  | Cost Threshold = |  | 100 | [13 empty] | By: | [7 empty] | Traffic:
Project Cost View |  |  | Round-Off = | 1 | [7 empty] | Short Term Daily Cost Table ($) | [6 empty] | Other: | [7 empty] | P/U: |  | 100% | [12 empty] | This sheet is used in the Users Guide, Ch. 1
[14 empty] | minutes | Period | 12-1A | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | 12-1P | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12
User Cost View |  |  | Period Cost View | [11 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Project: |  |  | Project: |  |  | Detailed Cost View
By: |  |  | By: |  |  | Project: |  |  | Method:
Other: |  |  | Other: |  |  | By: |  |  | Traffic: | [5 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
Method: |  |  | Method: |  |  | Other: |  |  | P/U: | 100%
Traffic: |  |  | Traffic: |  |  | Period (min): | Cost per Period |  |  |  |  | Long Term Daily Cost Table (Up to 24 hr) ($)
Period (min): | User Cost per Period |  | Period (min): | Cost per Period |  |  | 60 |  | 30 |  |  | Cost w/ Earlier Start |  |  | To | 12-1A: Hour-to-Hour Cost | To
| 60 | 30 |  | 60 | 30 | Time of Day | Period | Sum |  |  |  | + :30 |  |  | From | 1A | 2A | 3A | 4A | 5A | 6A | 7A | 8A | 9A | 10A | 11A | 12N | 1P | 2P | 3P | 4P | 5P | 6P | 7P | 8P | 9P | 10P | 11P | 12M | From
12 A - 1 A |  |  | 12 A - 1 A | 0 | 0 | 12 A - 1 A | 0 | 0 | 0 |  |  | 0 |  |  | 12M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12M
1 A - 2 A |  |  | 1 A - 2 A | 0 | 0 | 1 A - 2 A | 0 | 0 | 0 |  |  | 0 |  |  | 1A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1A
2 A - 3 A |  |  | 2 A - 3 A | 0 | 0 | 2 A - 3 A | 0 | 0 | 0 |  |  | 0 |  |  | 2A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2A
3 A - 4 A |  |  | 3 A - 4 A | 0 | 0 | 3 A - 4 A | 0 | 0 | 0 |  |  | 0 |  |  | 3A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3A
4 A - 5 A |  |  | 4 A - 5 A | 0 | 0 | 4 A - 5 A | 0 | 0 | 0 |  |  | 0 |  |  | 4A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4A
5 A - 6 A |  |  | 5 A - 6 A | 0 | 0 | 5 A - 6 A | 0 | 0 | 0 |  |  | 0 |  |  | 5A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5A
6 A - 7 A |  |  | 6 A - 7 A | 0 | 0 | 6 A - 7 A | 0 | 0 | 0 |  |  | 0 |  |  | 6A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6A
7 A - 8 A |  |  | 7 A - 8 A | 0 | 0 | 7 A - 8 A | 0 | 0 | 0 |  |  | 0 |  |  | 7A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7A
8 A - 9 A |  |  | 8 A - 9 A | 0 | 0 | 8 A - 9 A | 0 | 0 | 0 |  |  | 0 |  |  | 8A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8A
9 A - 10 A |  |  | 9 A - 10 A | 0 | 0 | 9 A - 10 A | 0 | 0 | 0 |  |  | 0 |  |  | 9A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9A
10 A - 11 A |  |  | 10 A - 11 A | 0 | 0 | 10 A - 11 A | 0 | 0 | 0 |  |  | 0 |  |  | 10A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10A
11 A - 12 P |  |  | 11 A - 12 P | 0 | 0 | 11 A - 12 P | 0 | 0 | 0 |  |  | 0 |  |  | 11A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11A
12 P - 1 P |  |  | 12 P - 1 P | 0 | 0 | 12 P - 1 P | 0 | 0 | 0 |  |  | 0 |  |  | 12N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12N
1 P - 2 P |  |  | 1 P - 2 P | 0 | 0 | 1 P - 2 P | 0 | 0 | 0 |  |  | 0 |  |  | 1P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1P
2 P - 3 P |  |  | 2 P - 3 P | 0 | 0 | 2 P - 3 P | 0 | 0 | 0 |  |  | 0 |  |  | 2P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2P
3 P - 4 P |  |  | 3 P - 4 P | 0 | 0 | 3 P - 4 P | 0 | 0 | 0 |  |  | 0 |  |  | 3P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3P
4 P - 5 P |  |  | 4 P - 5 P | 0 | 0 | 4 P - 5 P | 0 | 0 | 0 |  |  | 0 |  |  | 4P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4P
5 P - 6 P |  |  | 5 P - 6 P | 0 | 0 | 5 P - 6 P | 0 | 0 | 0 |  |  | 0 |  |  | 5P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5P
6 P - 7 P |  |  | 6 P - 7 P | 0 | 0 | 6 P - 7 P | 0 | 0 | 0 |  |  | 0 |  |  | 6P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6P
7 P - 8 P |  |  | 7 P - 8 P | 0 | 0 | 7 P - 8 P | 0 | 0 | 0 |  |  | 0 |  |  | 7P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7P
8 P - 9 P |  |  | 8 P - 9 P | 0 | 0 | 8 P - 9 P | 0 | 0 | 0 |  |  | 0 |  |  | 8P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8P
9 P - 10 P |  |  | 9 P - 10 P | 0 | 0 | 9 P - 10 P | 0 | 0 | 0 |  |  | 0 |  |  | 9P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9P
10 P - 11 P |  |  | 10 P - 11 P | 0 | 0 | 10 P - 11 P | 0 | 0 | 0 |  |  | 0 |  |  | 10P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10P
11 P - 12 A |  |  | 11 P - 12 A | 0 | 0 | 11 P - 12 A | 0 | 0 | 0 |  |  | 0 |  |  | 11P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11P
24 hr |  |  | 24 hr |  |  | 24 hr | 0 |  |  |  |  | + :30 |  |  |  | 1A | 2A | 3A | 4A | 5A | 6A | 7A | 8A | 9A | 10A | 11A | 12N | 1P | 2P | 3P | 4P | 5P | 6P | 7P | 8P | 9P | 10P | 11P | 12M
[14 empty] | Cost w/ | + :30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | + :30
[7 empty] | Examples | [6 empty] | Later
[7 empty] | 1:00P to 2:00P = | 0 |  | 1:30P to 2:00P = | 0 |  |  | Finish
[7 empty] | 1:00P to 3:00P: |  |  | 7:00A to 5:00P: |  |  | Examples Using Short Term Daily Cost Table |  |  | 12N: Examples Using Long Term Daily Cost Table
[7 empty] | 1:00P to 2:00P = | 0 |  | 12:00A to 5:00P = | 0 |  |  |  | 1:00P to 2:00P = | 1A: 0; 4A: 1:00P to 3:00P:; 8A: 1:30P to 2:30P:; 2P: 1:00P to 2:00P =; 3P: 0; 6P: 1:30P to 2:30P:; 10P: 6:30A to 5:30P:
[7 empty] | 2:00P to 3:00P = | 0 |  | -12:00A to 7:00A = | 0 |  |  |  |  | 4A: 1:00P to 2:00P =; 5A: 0; 8A: 1:30P to 2:00P =; 9A: 0; 2P: 7:00A to 5:00P =; 3P: 0; 6P: 1:30P to 2:00P =; 7P: 0; 10P: 7:00A to 5:00P =; 11P: 0
[8 empty] | 0 |  |  | 0 |  |  |  | 1:30P to 2:00P = | 1A: 0; 4A: 2:00P to 3:00P =; 5A: 0; 8A: 2:00P to 2:30P =; 9A: 0; 2P: 1:00P to 1:00P =; 3P: 0; 6P: 2:00P to 2:30P =; 7P: 0; 10P: 6:30A to 7:00A =; 11P: 0
[20 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  | 5:00P to 5:30P = | 0
[7 empty] | 1:30P to 2:30P: |  |  | 6:30A to 5:30P: | [5 empty] | 11P: 0
[7 empty] | 1:30P to 2:00P = | 0 |  | 7:00A to 5:00P = | 0 | [29 empty] | Note: | To hide unused columns, highlight them at top of spreadsheet, click left mouse button, click "hide"
[7 empty] | 2:00P to 2:30P = | 0 |  | 6:30A to 7:00A = | 0 | [30 empty] | To unhide unused columns, highlight columns to either side, click left mouse button, click "unhide"
[8 empty] | 0 |  | 5:00P to 5:30P = | 0 | [30 empty] | To hide/unhide unused rows, do the same as for columns, except do it for rows at left side of spreadsheet.
0
Project Cost View
[41 empty] | Project: |  |  | Period (1 hr) | 12 A - 1 A | 1 A - 2 A | 2 A - 3 A | 3 A - 4 A | 4 A - 5 A | 5 A - 6 A | 6 A - 7 A | 7 A - 8 A | 8 A - 9 A | 9 A - 10 A | 10 A - 11 A | 11 A - 12 P | 12 P - 1 P | 1 P - 2 P | 2 P - 3 P | 3 P - 4 P | 4 P - 5 P | 5 P - 6 P | 6 P - 7 P | 7 P - 8 P | 8 P - 9 P | 9 P - 10 P | 10 P - 11 P | 11 P - 12 A | Daily
By:
Other:
[41 empty] | Method: |  |  | Cost per Period ($/hr) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Lane-Closed Hours (hr) | Period Cost ($)
Traffic:
[41 empty] | P/U: | 100%
[41 empty] | Day | Date | Lane Closure Times | [11 empty] | Fraction of Hour Lane is Closed (hr)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
[41 empty] | Totals |  | Total Periods (hr) | [25 empty] | 0 | 0
[44 empty] | Total Cost ($) | [24 empty] | 0
Note on B15: Below, enter user cost for each period
Note on B16: Enter user cost for each period
Note on C15: Enter 15, 20, 30 (or blank, if shortest period = 60 min.)
Note on G6: Round-off for 60 min. blank (delete key) = no roundoff otherwise, $1, $10, $100, $1000
Note on H4: Default = 1 for user cost. For period cost, enter fraction = P/U = (period cost) / (user cost)
Note on H5: Threshold that period cost must exceed to be considered. User cost default = 0 (blank) Period cost default = $100.
Note on H6: Round-off for period = 15, 20, 30 min. blank (delete key) = no roundoff (default) otherwise $1, $10, $100, $1000
Go To
Print View
Print View with Example
Print
Print
Copy This Sheet
Paste Values
Print
Print
Detailed Cost
Daily Cost
Period Cost
Project Cost
Print
Print w/ Examples
User Cost
Daily Cost
Period Cost
Project Cost
Detailed Cost
User Cost
Detailed Cost
Daily Cost
Period Cost
User Cost
Period Cost
Project Cost
Paste Values
Print with Input

## constr
CONSTRUCTION COST SHEET | Project:
| By: |  |  | important
Other:
CONSTRUCTION COST | Standard Case | Alternative 1 | Alternative 2 | Alternative 3
General Input method
contract cost ($) |  | NA | NA | NA
lane-closed days (day) |  | NA | NA | NA
lane-closed days per work day | 1 | 1 | 1 | 1 | default.
lane-closed hours per day (hr/day)
relative productivity | 1 | 1 | 1 | 1 | default,
Labor Cost
labor cost % |  | NA | NA | NA
fixed mobilization (standard crew hr) | 0 | 0 | 0 | 0 | default.
shifts | 1 | 1 | 1 | 1 | default
crews per shift | 1 | 1 | 1 | 1 | default
workers per crew (relative) | 1 | 1 | 1 | 1 | default
productive hours per shift (hr)
paid hours per shift (hr) | 10 | 10 | 10 | 10 | default
% premium time | 0% | 0% | 0% | 0% | default
premium cost ($PT/$ST) | 1.4 | 1.4 | 1.4 | 1.4 | default
workers (relative) | 1 | 1 | 1 | 1
work days (day) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
lane-closed days (day) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
productive hours, total (hr) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
worker production hours, total (relative) | 0 | 0 | 0 | 0
paid hours, total (relative) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
cost per paid hour (relative) | 1 | 1 | 1 | 1
labor cost index | 1 | #DIV/0! | #DIV/0! | #DIV/0!
labor cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
labor cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Equipment Cost- Relative Based
equipment cost % |  | NA | NA | NA
relative number of items | 1 | 1 | 1 | 1 | default
equipment fixed cost/item, relative
equipment fixed cost, relative ($) | 0 | 0 | 0 | 0
equipment cost/day/item, relative
equipment cost ($) (day based)* | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost/hr/item, relative | 1 | 1 | 1 | 1 | default
equipment cost ($) (hr based)* | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost, relative ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost difference, relative ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Equipment Cost - Total Based
relative number of items
equipment fixed cost/item, total
equipment fixed cost, total ($) | 0 | 0 | 0 | 0
equipment cost/day/item, total
equipment cost, total ($) (day based)* | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost/hr/item, total
equipment cost,total ($) (hr based)* | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost,total ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
equipment cost difference, total ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Material Cost
material cost ($)
materal cost difference ($) | na | 0 | 0 | 0
Traffic Maintenance Cost
traffic maintenance fixed cost ($)
traffic maintenance daily cost ($/day)
traffic maintenance hourly cost ($/hr)
traffic maintenance total cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
traffic maintenance cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Other Contract Cost
other % cost (%)
other fixed cost ($)
other daily cost ($/day)
other hourly cost ($/hr)
other total cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
other total cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Agency Cost
agency % cost (%)
agency fixed cost ($)
agency daily cost ($/day)
agency hourly cost ($/hr)
agency total cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
agency cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Total Construction Cost
contract cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
contract cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
project cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
project cost difference ($) | na | #DIV/0! | #DIV/0! | #DIV/0!
Summary method
lane-closed hours per day (hr/day)
lane-closed days (day) |  | #DIV/0! | #DIV/0! | #DIV/0!
labor cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
project cost ($) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
*Generally do not use both hr based and day based equip cost.
Note on A8: Default = 1 for daily closure. Default > 1 for 24 hr closure.
Note on A10: Default = 1
Note on A12: Labor cost with lanes closed for this work as percent of contract cost.
Note on A13: Default: 0. May be significant for 24 hr closures.
Note on A16: Default: 1
Note on A17: Generally, this is less than paid hours per shift for daily closure. Default = paid hours per shift for 24 hr closure.
Note on A18: Defaults: 8 or 10 hours per day.
Note on A19: Default: 0 for 5x8 hour days or 4x10 hour days per week.
Note on A20: Default: 1.4 for time and a half.
Note on A31: Equipment cost does not change significantly for many projects. Adjust equipment costs only when it is important. Generally use Relative Based where you do not itemize equipment and Total Based where you estimate cost of individual items of equipment.
Note on A32: Input fraction of contract cost that is equipment.
Note on A33: Default = 1
Note on A42: Equipment cost does not change significantly for many projects. Adjust equipment costs only when it is important. Generally use Relative Based where you do not itemize equipment and Total Based where you estimate cost of individual items of equipment.
Note on A43: Default = 1
Note on A52: Material cost does not change on most projects. Use this only when the material requirements change.
Note on A55: Traffic Maintenance changes are not important on most projects. Use this part only when differences will be significant.
Note on A61: Other contract cost changes are not important on most projects. Use this part only when differences will be significant.
Note on A62: % increase (or decrease) in contract cost not in other variables. Default = blank for day work. Default = 10% * (1-labor cost %) for night work.
Note on A68: Agency cost changes are not important on most projects. Use this part only when differences will be significant.
Note on C28: Standard Case is always 1.
Copy This Sheet
You can paste these values into Impact Sheet.