## QAQC Review Process by Template
QA/QC REVIEW PROCESS BY TEMPLATE - 02/13/2025
This table should be used to determine the QA/QC Process to be followed when developing a project. | [6 empty] | 36
When multiple projects are packaged together in one proposal, the higher level process must be used.
Template | Plan | FPC | OEC | Certification | Advertising
Description | Review | Meeting | by QA & Lettings | Acceptance | Period
| Required | Required | Prior to Turn-In | Form | (Weeks)
Bridge - Big Bridge Program | Yes | Yes | No | Type - 1 | 5
Bridge - Blue Water Bridge | Yes | Yes | No | Type - 1 | 5
Bridge - Preservation & Replacement - Type 1 (3) | Yes | Yes | No | Type - 1 | 5
Bridge - Preservation & Replacement - Type 2 (3) | No | No | Yes | Type - 2 | 3
Bridge-RFA | No | No | Yes | Type - 2 | 3
Bridge - Special Needs - Type 1 (3) | Yes (2) | Yes | No | Type - 1 | 5
Bridge - Special Needs - Type 2 (3) | No | No | Yes | Type - 2 | 3
Capacity Improvement | Yes | Yes | No | Type - 1 | 5
Carbon Reduction (Rural) | Yes | Yes | No | Type - 1 | 5
Carpool Parking Lot Program | Yes | Yes | No | Type - 1 | 5
Commercial Vehicle Enforcement | Yes | Yes | No | Type - 1 | 5
Congestion Mitigation and Air Quality (CMAQ) | Yes | Yes | No | Type - 1 | 5
Culvert - Capital - Type 1 | Yes | Yes | No | Type - 1 | 5
Culvert - Capital - Type 2 | No | No | Yes | Type - 2 | 3
Culvert - Road-RFA | No | No | Yes | Type - 2 | 3
Discretionary | Yes | Yes | No | Type - 1 | 5
Economic Development | Yes | Yes | No | Type - 1 | 5
Freeway Lighting | Yes | Yes | No | Type - 1 | 5
Freeway Operations | Yes | Yes | No | Type - 1 | 5
Freeway Resurfacing Program (FRP) - Type 1 (3) | Yes | Yes | No | Type - 1 | 5
Freeway Resurfacing Program (FRP) - Type 2 (3) | No | No | Yes | Type - 2 | 3
Heavy Maintenance | No | No | Yes | Type - 2 | 3
Intelligent Transportation Systems - Capital | Yes | Yes | No | Type - 1 | 5
Intelligent Transportation Systems - Operations | Yes | Yes | No | Type - 1 | 5
IT System Development | Yes | Yes | No | Type - 1 | 5
Jurisdictional Transfer | Yes | Yes | No | Type - 1 | 5
Michigan Institutional Roads (MIR) | Yes | Yes | No | Type - 1 | 5
New Roads | Yes | Yes | No | Type - 1 | 5
Noise Abatement | Yes | Yes | No | Type - 1 | 5
Non-Freeway Resurfacing Program (NFRP) | No | No | Yes | Type - 2 | 3
Operations | Yes | Yes | No | Type - 1 | 5
Passing Relief Lanes (PRL) | Yes | Yes | No | Type - 1 | 5
Pump Station Rehabilitation | Yes | Yes | No | Type - 1 | 5
Railroad Crossings Program | Yes | Yes | No | Type - 1 | 5
Recreational Trails | Yes | Yes | No | Type - 1 | 5
Rest Areas | Yes (2) | Yes | No | Type - 1 | 5
Road - Capital Preventive Maintenance (CPM) | No | No | Yes | Type - 2 | 3
Road - Rehabilitation and Reconstruction (R&R) | Yes | Yes | No | Type - 1 | 5
State Funded Required Programs | Yes (2) | Yes | No | Type - 1 | 5
State Railroad Crossings Program | Yes | Yes | No | Type - 1 | 5
Statewide Heavy Maintenance | No | No | Yes | Type - 2 | 3
Traffic & Safety - Delineators | (1) | (1) | No | Type - 3 | 5
Traffic & Safety - Pavement Markings | (1) | (1) | No | Type - 3 | 5
Traffic & Safety - Safety Programs | Yes | Yes | No | Type - 1 | 5
Traffic & Safety - Signs | (1) | (1) | No | Type - 3 | 5
Traffic Signal - Modernization | (1) | (1) | No | Type - 3 | 5
Traffic Signal - New Signals | (1) | (1) | No | Type - 3 | 5
Transportation Alternatives | Yes | Yes | No | Type - 1 | 5
Trunkline Modernization | Yes | Yes | No | Type - 1 | 5
Wetland Pre-Mitigation | Yes | Yes | No | Type - 1 | 5
(1) QA/QC review process/procedure by Traffic and Safety
(2) Plan Review Meeting is optional
(3) Select based on Work Type Code. See Work Type Code tab
● Plan Reviews on Superior Region projects classified as FHWA must be conducted by QA & Lettings; others by Project Manager
● On projects with a programmed cost of <$100,000, the Project Manager may conduct the Plan Review Meeting
● When projects with different templates are packaged, the more extensive review process must be followed
● Whenever the Project Manager conducts the Plan Review Meeting, minutes of the meeting must be included in ProjectWise
● Whenever The Plan Review & FPC Meetings are combined, minutes of the meeting must be included in ProjectWise
● Any deviation from the above procedures must have a signed Exception to the Process (form 0334) included in ProjectWise
PLEASE MAKE SURE ALL DROPDOWNS ARE SET TO 'YES' OR 'N/A' PRIOR TO PROJECT MANAGER SIGNING

## Work Type Codes
For Bridge Preservation and Replacement Projects Only
Work Type Codes that require a Type 1 CA Form |  | Work Type Codes that require a Type 2 CA Form
432 | Asphalt cap (no membrane) | 468 | Approach Pavement Relief Joints
434 | Asphalt overlay w/waterproofing membrane | 714 | Bearing Realignment
623 | Bridge Approach | 619 | Bridge Barrier Railing Repair
618 | Bridge Barrier Railing Replace | 465 | Concrete Surface Coating
474 | Bridge Removal | 466 | Crack Sealing
221 | Bridge Replacement | 419 | Deck Patching
452 | Culvert Replacement | 617 | Deck Patching - Full Depth
130 | Deck Replacement | 462 | Drain System Clean/Repair
470 | Miscellaneous Bridge | 479 | Healer Sealer
421 | Miscellaneous Bridge CPM | 464 | Joint Repair
139 | Miscellaneous Rehabilitation | 430 | Joint Replacement
234 | Miscellaneous Replace | 624 | Metal Mesh Panels
341 | New Structure on Existing Route | 467 | Minor Concrete Patching
311 | New Structure on New Route | 476 | Miscellaneous Bridge CSM
321 | New Structure on Relocated Route | 418 | Overlay - Epoxy
471 | New Technologies | 463 | Paint - Spot
424 | Overlay - Deep | 433 | Painting - Zone
417 | Overlay - Shallow | 469 | Slope Protection Repair
422 | Painting Complete | 431 | Substructure Patching
423 | Pin & Hanger Replacement | 116 | Substructure Repair
478 | Relocation of Railroad Facilities | 622 | Superstructure Repair - Concrete
420 | Scour Protection | 621 | Superstructure Repair - Steel
475 | Special Needs | 460 | Superstructure Wash
117 | Substructure Replacement | 620 | Thrie Beam Retrofit
137 | Superstructure Replacement | 461 | Vegetation Control
230 | Widen - Add Lanes
135 | Widen-Maintain Lanes
For Freeway Resurfacing Projects Only
684 | Milling and Two Course Asphalt Resurfacing | 408 | Milling & One Course Asphalt Overlay
|  | 450 | Full Depth Concrete Pavement Repair